## Release Plan
Sprint 1 - Release day: 01/03/2022
Scope of delivery | UML Diagram
DFD
Sitemap
Use case diagram
UI prototype
ERD Diagram
Action flow
Sprint 2 - Release day: 09/03/2022
Scope of delivery | Homepage
Routing pages funtion
Create/edit posts page [UI]
Sort dropdown [UI]
Overview posts page
Profile page
View posts details page
APIs
Sprint 3 - Release day: 15/03/2022
Scope of delivery | Create/edit posts page [Function]
React to posts
Comment to post
View count on each post
Report page
Test plan
Sprint 4 - Release day: 22/03/2022
Scope of delivery | Test cases
Create report algorithm